## Coverpage
Name: |  |  |  | Jacket Zheng Chen |  |  | Semester start: | 2025-08-27
Section: |  |  |  | CISC 4900
Total Hours: |  |  |  | 38.5
Week | Start | End | Supervisor discussion | Team discussion | Design | Coding | Documentation | Testing & Debugging | Research, Training, Learning | Other | Total Hours for the week
1 | 2025-08-27 | 2025-09-02 | 2 | 4 | 1 | 0 | 1 | 0 | 3 | 4 | 15
2 | 2025-09-03 | 2025-09-09 | 1 | 2.5 | 2 | 0 | 5 | 2 | 0.5 | 2 | 15
3 | 2025-09-10 | 2025-09-16 | 0 | 0 | 2.5 | 0 | 0 | 0 | 4 | 2 | 8.5
4 | 2025-09-17 | 2025-09-23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | [10 empty] | 0
6 | [10 empty] | 0
7 | [10 empty] | 0
8 | [10 empty] | 0
9 | [10 empty] | 0
10 | [10 empty] | 0
11 | [10 empty] | 0
12 | [10 empty] | 0
13 | [10 empty] | 0
14 | [10 empty] | 0
15 | [10 empty] | 0
16 | [10 empty] | 0
Total |  |  | 3 | 6.5 | 5.5 | 0 | 6 | 2 | 7.5 | 8 | 38.5
Formulas:
Start = [Start, row above]+7
End = [Start]+6

## Timelog
Date | Duration (hours) | Category | Description of completed task | Challenges and/or next steps | Reflection
2025-08-27 | 0.5 | Documentation | Reviewed the requirements for this class, the due dates and started early talks with my group about our future project
2025-08-28 | 1.5 | Research, Training, Learning | Researched ideas for the project
2025-08-29 | 1.5 | Research, Training, Learning | Learning more about different topics that could be used
2025-08-29 | 0.5 | Documentation | Potential topics are written down
2025-08-30 | 2 | Supervisor Discussion | Meeting with our supervisor for plan
2025-08-31 | 4 | Team Discussion | Brainstorm ideas with my team in person and on discord
2025-08-31 | 1 | Design | Small ideas and outline for the project
2025-09-01 | 4 | Other | Self-learning new potential tools, and learning more about the job market |  | Need to be working more toward improving the resume, and getting some certificates
2025-09-03 | 1 | Team Discussion | Discussion with the group
2025-09-03 | 0.5 | Research, Training, Learning | Learned more about github and the potential uses
2025-09-03 | 2 | Other | Internships/jobs reviews
2025-09-03 | 1 | Supervisor Discussion | Ideas discussion and advice were taken from the supervisor
2025-09-04 | 2.5 | Research, Training, Learning | Ideas research
2025-09-04 | 1.5 | Team Discussion | Discord meeting
2025-09-04 | 1.5 | Testing & Debugging | No coding yet, just testing files
2025-09-07 | 5 | Documentation | Writing down ideas discussed during the meeting | Ideas are coming in, we might have to narrow it down
2025-09-10 | 2.5 | Design | Small design ideas
2025-09-10 | 2 | Research, Training, Learning | Learned more about mongoDB | Confusing, but manageable
2025-09-11 | 2 | Research, Training, Learning | More learning about mongoDB
2025-09-11 | 2 | Other | Personal reflection